## Slide 1
Continuous Improvement Plan for PEEL
January 2025 - 2026

## Slide 2: Update to Framework – Key Information
Introduce two new core questions (on safeguarding and the response to fraud);
Move the inspection of custody into PEEL, which will increase the frequency of
inspections, so every force is inspected every four (rather than six) years;
Make changes to how we inspect and report on crime data integrity and the
management of suspects and offenders; and
Change elements of the HMI summary.
Notes: Recommendation 2:
The Government has confirmed funding for a new Centre for Police Productivity which will be based in the College of Policing. This will be established from autumn 2024. We wait to see what this will being centrally and feedback to CIB.
Recommendation 8:
As a force we might be a little behind the curve on this. Mandy Rowlatt / Sarah Peart & Roy Cowper attended a College of Policing Led online briefing regarding auto-redaction last week – this highlighted good practice across many forces who have already got contracts in place. The example tool that was demonstrated outlined 80-90% time savings; case files alone minimum of 618,000 officer hours saved if all forces switched on auto redaction. It is clear we have to make this a Digital Priority with C&J if not already.
Recommendation 12:
The Home Office continues to work closely with the Review team and other policing partners (including NPCC, College of Policing, HMICFRS, the Chief Medical Officer for Policing and the Police Federation of England and Wales (PFEW)) to ensure that forces have the data and best practice required to make informed decisions on how best to deploy their workforce and manage the level of sickness absence. The Centre for Police Productivity will be critical in ensuring forces own and use high quality data to support these decisions in the future
The Home Office are keen to see the findings and recommendations which result from the ongoing work of the Review Team and have created a sector-wide working group to identify best practice and existing data collection in relation to limited duties and sickness absence. The Home Office will continue to work with the sector to enable forces to improve resilience by deploying officers in a more efficient way and ensure modernised and fair adjustments for officers.

## Slide 3
 | WORK DELIVERED COLLECTIVELY SO FAR: | Apr 2024 | May 2024 | June 2024 | July 2024 | Aug 2024 | Sept 2024 | Oct 2024 | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025 | Mar 2025
STRATEGY | Planning | Review of all Strategic Documents | FMS Published |  |  |  |  |  |  |  |  |  | 
 | Engagement |  |  | SLT Away day & Federation Consultation | 121 consultation with Leadership Team |  |  |  |  |  |  |  | 
 | Plan on a Page |  |  | Draft plan on a page requirements formulated & tested through force governance structure (FEM) & Leadership Days for wider Supt & Staff Leader input |  |  |  |  |  |  |  |  | 
 | Socialisation & Implementation |  |  |  |  |  | Leadership Day |  | First Line Manager Leadership Events |  |  |  | 
CONTINUOUS IMPROVEMENT PLAN | Workstream 1 Tracking Progress and Oversight - AFIs | Monthly monitoring and tracking across all force level governance structures |  |  |  |  |  |  |  |  |  |  | 
 | Workstream 2 Business Assurance Activity | Sudden Death, Robbery, Crime Cancellations, Outcome 14/15/ 16, NCPI preparedness, Custody HMICFRS preparedness. |  |  | PDM Quality, Missed Outcome Opportunities, Effective response to crime reports from MH settings. |  |  |  |  |  |  |  | 
 |  | OC 17 Oversight Victim Satisfaction – Vehicle Crime, violent crime, ASB, Hate Crimes, Burglary, Crime Allocation Policy, CDI internal Assessment |  |  | Victim Satisfaction – Vehicle Crime, violent crime, ASB, Hate Crimes, Burglary, Crime Allocation Policy, CDI internal Assessment |  |  | OC 17 Oversight, Victim Satisfaction – Vehicle Crime, violent crime, ASB, Hate Crimes, Burglary, Crime Allocation Policy, CDI internal Assessment |  |  | OC 17 Oversight, Victim Satisfaction – Vehicle Crime, violent crime, ASB, Hate Crimes, Burglary, Crime Allocation Policy, CDI internal Assessment |  | 
 | Workstream 3 Self-Assessment (PAF workbooks) |  |  | PAF Review leads identified & workstream will deliver 9 Full end to end reviews against PEEL assessment criteria. |  |  |  |  |  |  |  |  | 
 | Workstream 4 Dedicated Review of Investigating Crime | Scoping, allocation of resources & identification of force lead. E2E DA review, LP workload review & workshop planning |  |  |  |  | VSA Crime File Audit (to support review) |  |  |  |  |  | 
 | Workstream 5 Understanding Demand & Resourcing |  | FMS Published | Restructure SPB | Dept level force wide demand assessment (Dec Deadline), VFM profiles & PAF 9 review (Sept deadline) |  |  |  |  | Dept level force wide demand assessment |  |  | 
 | Workstream 6 Force Strategy, Structure & Governance |  | Stability in Leadership | Leadership Day | Revised Corp Governance |  | Revised Force Strategy |  |  |  |  |  | 

## Slide 4: Next Steps
HMICFRS will commence fieldwork from April (exact dates to be confirmed but they have requested meeting invitations now). The following next steps are proposed to prepare for PEEL:
Update all PAF reviews to reflect new & amended questions in revised Framework and identify any gaps in work already delivered
Strengthen Audit/ Assurance through reality testing and focus groups led by us (HMICFRS have given a clear indication they expect to see this & we were unable to provide evidence through NCPI).
Prepare work in PAF question order and use as template for future CIB meetings – our FLL will review each PAF question in this way between April and December.
Strategy and Innovation to lead some “how will you be assessed” sessions for Chief Superintendents and/or their existing governance structures to set out:
    DAP measures – so you can see exactly what data HMICFRS will assess you against through inspection
    Any outliers you may not be aware of through current performance reporting (this may be because of point in time or it not being an identified priority)
    Progress against recommendations in previous PAF reviews
    Reality testing plan & feedback plan for findings (collaborative).
Notes: Recommendation 2:
The Government has confirmed funding for a new Centre for Police Productivity which will be based in the College of Policing. This will be established from autumn 2024. We wait to see what this will being centrally and feedback to CIB.
Recommendation 8:
As a force we might be a little behind the curve on this. Mandy Rowlatt / Sarah Peart & Roy Cowper attended a College of Policing Led online briefing regarding auto-redaction last week – this highlighted good practice across many forces who have already got contracts in place. The example tool that was demonstrated outlined 80-90% time savings; case files alone minimum of 618,000 officer hours saved if all forces switched on auto redaction. It is clear we have to make this a Digital Priority with C&J if not already.
Recommendation 12:
The Home Office continues to work closely with the Review team and other policing partners (including NPCC, College of Policing, HMICFRS, the Chief Medical Officer for Policing and the Police Federation of England and Wales (PFEW)) to ensure that forces have the data and best practice required to make informed decisions on how best to deploy their workforce and manage the level of sickness absence. The Centre for Police Productivity will be critical in ensuring forces own and use high quality data to support these decisions in the future
The Home Office are keen to see the findings and recommendations which result from the ongoing work of the Review Team and have created a sector-wide working group to identify best practice and existing data collection in relation to limited duties and sickness absence. The Home Office will continue to work with the sector to enable forces to improve resilience by deploying officers in a more efficient way and ensure modernised and fair adjustments for officers.

## Slide 5
PROPOSED 2025 – 2027 PLAN: | Mar 2025 | Apr 2024 | May 2024 | June 2024 | July 2024 | Aug 2024 | Sept 2024 | Oct 2024 | Nov 2024 | Dec 2025
VSA Audit |  | Mini VSA conducted & findings to May CIB |  |  |  |  | Mini VSA revisited & findings to Oct CIB |  |  | 
Q1. Leadership | Review Reality Testing/ Focus Groups | Present to CIB |  |  |  |  |  |  | DOCUMENT REQUEST READINESS | INSPECTION PREPARATION PERIOD
Q2. supporting and developing the workforce | Review Reality Testing/ Focus Groups | Present to CIB |  |  |  |  |  |  |  | 
Q3. public treatment |  | Review Reality Testing/ Focus Groups | Present to CIB |  |  |  |  |  |  | 
Q4. prevention and deterrence |  | Review Reality Testing/ Focus Groups | Present to CIB |  |  |  |  |  |  | 
Q5. responding to the public |  |  | Review Reality Testing/ Focus Groups | Present to CIB |  |  |  |  |  | 
Q6. investigating crime |  |  | Reality Testing/ Focus Groups | Present to CIB |  |  |  |  |  | 
Q7. safeguarding children and adults at risk |  |  |  | Review Reality Testing/ Focus Groups | Present to CIB |  |  |  |  | 
Q8. managing fraud |  |  |  | Review Reality Testing/ Focus Groups | Present to CIB |  |  |  |  | 
Q9. a safe and lawful custody environment |  |  |  |  | Review Reality Testing/ Focus Groups | Present to CIB |  |  |  | 

## Slide 6: Leads
PAF Area | SRO / Senior Officer Lead | S&I Lead
Q1. Leadership | DCC Tuckley / Several | Colleen Rattigan
Q2. Supporting and developing the workforce | ACO Bullen / Suzanne McMinn | Jenny Cheney
Q3. Public treatment | ACC Ward / CS Hillery | Sarah Peart
Q4. Prevention and deterrence | ACC Ward / CS Hillery | Gareth Court
Q5. Responding to the public | ACC Ward / DCS Helm | Gareth Court
Q6. Investigating crime | ACC James / DCS Tompkins | Jenny Cheney
Q7. Safeguarding children and adults at risk | ACC James / DCS Rymarz | Colleen Rattigan
Q8. Managing fraud | ACC James / DCS Tompkins | Sarah Peart
Q9. A safe and lawful custody environment | ACC Ward / DCS Helm | Tbc
Notes: Recommendation 2:
The Government has confirmed funding for a new Centre for Police Productivity which will be based in the College of Policing. This will be established from autumn 2024. We wait to see what this will being centrally and feedback to CIB.
Recommendation 8:
As a force we might be a little behind the curve on this. Mandy Rowlatt / Sarah Peart & Roy Cowper attended a College of Policing Led online briefing regarding auto-redaction last week – this highlighted good practice across many forces who have already got contracts in place. The example tool that was demonstrated outlined 80-90% time savings; case files alone minimum of 618,000 officer hours saved if all forces switched on auto redaction. It is clear we have to make this a Digital Priority with C&J if not already.
Recommendation 12:
The Home Office continues to work closely with the Review team and other policing partners (including NPCC, College of Policing, HMICFRS, the Chief Medical Officer for Policing and the Police Federation of England and Wales (PFEW)) to ensure that forces have the data and best practice required to make informed decisions on how best to deploy their workforce and manage the level of sickness absence. The Centre for Police Productivity will be critical in ensuring forces own and use high quality data to support these decisions in the future
The Home Office are keen to see the findings and recommendations which result from the ongoing work of the Review Team and have created a sector-wide working group to identify best practice and existing data collection in relation to limited duties and sickness absence. The Home Office will continue to work with the sector to enable forces to improve resilience by deploying officers in a more efficient way and ensure modernised and fair adjustments for officers.

## Slide 7: Thematic Inspections
In 2024/25 and complete them in 2025/26:
Firearms Licensing
Police Leadership
In the next 4 years:
Joint Inspection on Knife Crime
Efficiency and effectiveness of current arrangements that provide local, regional and national policing services (includes PDS & NPAS)
Science and Technology
Economic Crime
Undercover Policing
Police and Fire Service Cyber Security
Counter Terrorism
JESIP
Data and Analytics
SOC – Regional Inspection will continue
Integrity – Continue as rolling inspection
VAWG – Monitored through several inspections (NCPI, PEEL).
Super Complaints – expected to be different in approach and investigations
Notes: Recommendation 2:
The Government has confirmed funding for a new Centre for Police Productivity which will be based in the College of Policing. This will be established from autumn 2024. We wait to see what this will being centrally and feedback to CIB.
Recommendation 8:
As a force we might be a little behind the curve on this. Mandy Rowlatt / Sarah Peart & Roy Cowper attended a College of Policing Led online briefing regarding auto-redaction last week – this highlighted good practice across many forces who have already got contracts in place. The example tool that was demonstrated outlined 80-90% time savings; case files alone minimum of 618,000 officer hours saved if all forces switched on auto redaction. It is clear we have to make this a Digital Priority with C&J if not already.
Recommendation 12:
The Home Office continues to work closely with the Review team and other policing partners (including NPCC, College of Policing, HMICFRS, the Chief Medical Officer for Policing and the Police Federation of England and Wales (PFEW)) to ensure that forces have the data and best practice required to make informed decisions on how best to deploy their workforce and manage the level of sickness absence. The Centre for Police Productivity will be critical in ensuring forces own and use high quality data to support these decisions in the future
The Home Office are keen to see the findings and recommendations which result from the ongoing work of the Review Team and have created a sector-wide working group to identify best practice and existing data collection in relation to limited duties and sickness absence. The Home Office will continue to work with the sector to enable forces to improve resilience by deploying officers in a more efficient way and ensure modernised and fair adjustments for officers.

## Slide 8: Fighting Crime, Protecting People