## Slide 1: HMICFRS PEEL AFIs – Governance and progress
AFI | Business Lead | SRO | Governance
The force needs to improve how it records equality data. | Sarah Crampton | Paul Bullen | Force Assurance Board
The force needs to consistently record and evaluate day-to-day problem solving and share learning. | Ch Supt Hillery | ACC Ward | Prevention and Intervention Board
The force needs to improve the time it takes to answer emergency calls. | Ch Supt Helm | ACC Ward | Local Policing Performance Board
The force needs to attend calls for service in line with published attendance times and make sure the caller is updated if there are delays. | Ch Supt Helm | ACC Ward | Local Policing Performance Board
The force should make sure it allocates investigations to officers and teams that have the capability and capacity to carry out timely and thorough investigations. | D/Ch Supt Rymarz | ACC James | Project Sherlock
The force isn’t always achieving outcomes for victims of crime. | D/Ch Supt Rymarz | ACC James | Project Sherlock
The force needs to make sure it is using outcomes appropriately and that these outcomes comply with force and national policies. | D/Ch Supt Rymarz | ACC James | Project Sherlock
The force should put reliable processes in place to monitor protective orders and make sure that breaches are prioritised to safeguard the victim. | D/CH Supt Tompkins | DCC Tuckley | Vulnerability Board

## Slide 2: HMICFRS PEEL AFIs – Governance Cont.
AFI | Business Lead | SRO | Governance
Police representatives at multi-agency risk assessment conferences should have sufficient knowledge and experience to agree actions that reduce harm, on behalf of the force. | DCh/Supt Tompkins | ACC James | Vulnerability Board
The force should make sure that Violent and Sex offender Register supervisory reviews are of a high quality and that officers raise and complete actions. These reviews should include comprehensive intelligence checks to effectively manage the risk posed by registered sex offenders. | DCh/Supt Tompkins | ACC James | Vulnerability Board
The force should make sure it has the capacity and capability to manage the demand in the online child abuse investigations unit to avoid delays in enforcement action being taken. Supervisors should review caseloads and make sure offender managers regularly review available intelligence. | DCh/Supt Tompkins | ACC James | Vulnerability Board
The force needs to improve its understanding of why new recruits leave the force. | Suzanne McMinn | ACO Bullen | People and Culture Board
The force needs to do more to support the development and career progression of people from under-represented groups. | Suzanne McMinn | ACO Bullen | People and Culture Board
The force needs to establish processes to regularly review its strategic decisions, policies and processes to check they are effective and provide the intended outcome. | Colleen Rattigan | CC Balhatchet | Strategic Planning Board
The force has invested in its IT to provide better access to data. But senior leaders need to provide effective governance to maximise the potential for technology to increase productivity. | Paul Bullen | CC Balhatchet | Strategic Planning Board
The force needs to reduce the number of non-emergency calls the caller abandons because they aren’t answered | Ch/Supt Helm | ACC Ward | Local Policing Performance

## Slide 3: High – level AFI update:
Victim data –Technology review sits within the Data Quality Working group. Next steps will be to look at training/education for officers, giving confidence to capture data correctly. Governance for this AFI will sit within Force Assurance Board.
Problem Solving – lots of work being developed to include training, education, development of scrutiny panels, enhance pages on Forcenet. Resource bid greed in December. TOR for P&I Board being created.
Emergency calls – Improved picture over the summer and continue to be in the top 10 forces for performance.
Attendance times – Goodsam technology now deployed to support with this. Review of processes within FCR completed such as “re-thrive”. Benchmarking completed with MSG and we performed second best in relation to response time for G1 Urban and rural, but 5th for G2 responses. Gold Group set up to manage this. Business Insights reviewing metrics. Text message trial started in Jan 25.
Capability and capacity of investigators – Crime Allocation policy reviewed, and a number of proposals already put forward by Project Sherlock. Training to be reviewed and looking to develop a Probationer Development unit to better support new recruits. Agreement obtained to recruit PSIs to support front line.
Outcome for victims – This forms part of Project Sherlock – work being undertaken to review and understand data. Outcomes are also discussed in Strategic Justice Board. Introducing a Priority Crime team, ongoing reviews of crimes to identify learning and good practice.
Outcomes used correctly – This sits within Strategic Justice Board and Project Sherlock – regular audit activity carried out by FCIR team, BTI assurance activity completed and work ongoing in CJ Command around educating officers.
Proactive Orders – DAIU being progressed and Qlik app now in place to support with managing orders. Force has had good success with order applications. CE Hub also has process in place for compliance checks. New team is now in place (Proactive team) who focus on orders. Breaches are proactively responded to by LPA or dedicated teams, depending on type of breach.

## Slide 4
9. Attendance at MARAC – This forms part of the DAIU Working Group to look at processes for DA. DA Manager due to take up role at the end of Fed. All MARACs have DAIU present and had appropriate training.
10. Supervisor reviews Violent and Sex offender investigations – intelligence checks are now completed routinely, and process is embedded. Time has been freed up for supervisors to complete better quality file reviews. Processes well embedded.
11. Demand is OCAIU – much improved position with daily management of outstanding enforcement, recruitment completed and VCOP compliance high.
12. Understanding why recruits are leaving – Lots of activity through People and Culture Board including; Is your future with us, Say and Stay, review of exit interview process with changes as a result, report on retention presented to Board. New tutoring process approved at FEM. New recruitment material has been created to explain role of a police officer.
13. Progression of underrepresented groups – Careers Academy being rolled out, research completed with groups to understand what can be done to better support progression. Phase 1 had positive results. Phase 2 being rolled out imminently.
14. Review Strategic Decisions – Plan on a Page and Policing Plan will inform a lot of this work. Process for Policies, Procedures and Strategies is well embedded through management within S&IU.
15. Leaders to maximise technology to improve productivity – Qlik Apps being reviewed to cleanse systems. Police Productivity Review presented to FEM with owners aligned to recommendations. All digital projects sit on Portfolio Tool, Benefits Realisation Manager role filled. Business Capability review and road mapping work is underway.
16. Abandonment rate – Plans progressing and performance is improving. Goodsam should support with this.; phase 1 underway, phase 2 started in Jan where some selected DA cases are offered a telephone consultation. Phase 3 to be rolled out later in the year which includes other offence types.