### AGENDA ITEM 7

### Report to the Joint Independent Audit Committee

### 04 March 2026

Internal Audit Recommendations Summary Report

RECOMMENDATION

The Committee is asked to note this report.

### PURPOSE OF THE REPORT

  - This report provides the Joint Independent Audit Committee (JIAC) with an update on the status of actions arising from recommendations made in internal audit reports.

  - The report contains actions arising from audits of Northamptonshire Police and the Office of Northamptonshire Police, Fire and Crime Commissioner and East Midlands Collaboration Units. Where joint police and fire audits have been undertaken all recommendations are included in this report irrespective of whether they apply solely to police or fire or if they apply jointly to both organisations.

  - The attached Summary of Internal Audit Recommendations Report shows details and the current status of all open audit actions.

  - The Risk, Audit and Assurance Board has oversight of all outstanding audit actions and directs the activities required to complete any actions that have passed their targeted implementation date.

- NORTHAMPTONSHIRE AUDITS

  - Overall Status

Overview of completed internal audits and recommendations by audit year.

| 2023/24 Audits | Date | Grade | Recommendations |  |  |  |  |  |  | Overall Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Priority 1 | Priority 2 | Priority 3 | Progress |  |  |  |  |
|  |  |  |  |  |  | Overdue | Revised | Ongoing | Closed |  |
| Firearms Licensing | 21 July 2023 | Moderate Assurance | 0 | 2 | 0 | 0 | 0 | 0 | 2 |  |
| RUI Follow Up | 26 September 2023 | Moderate Assurance | 0 | 1 | 2 | 0 | 0 | 0 | 3 |  |
| Business Continuity & Emergency Planning | 01 November 2023 | Limited Assurance | 2 | 3 | 0 | 0 | 0 | 0 | 5 |  |
| Reasonable Adjustments Follow Up | 25 January 2024 | Moderate Assurance | 0 | 2 | 3 | 0 | 0 | 0 | 5 |  |
| Core Financials | 06 March 2024 | Moderate Assurance | 0 | 3 | 3 | 0 | 0 | 0 | 6 |  |
| Vetting | 18 March 2024 | Moderate Assurance | 0 | 1 | 2 | 0 | 0 | 0 | 3 |  |
| Fleet Management Follow Up | 25 April 2024 | Moderate Assurance | 0 | 0 | 3 | 0 | 0 | 0 | 3 |  |
| Payroll | 01 May 2024 | Moderate Assurance | 0 | 3 | 0 | 0 | 0 | 0 | 3 |  |
| Identity Access Management | 11 June 2024 | Limited Opinion | 0 | 5 | 1 | 0 | 2 | 0 | 4 |  |
| IT Asset Legacy Management | 11 June 2024 | Moderate Opinion | 0 | 2 | 3 | 0 | 0 | 0 | 5 |  |
| Totals |  |  | 2 | 22 | 17 | 0 | 2 | 0 | 39 |  |

| 2024/25 Audits | Date | Grade | Recommendations |  |  |  |  |  |  | Overall Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Priority 1 | Priority 2 | Priority 3 | Progress |  |  |  |  |
|  |  |  |  |  |  | Overdue | Revised | Ongoing | Closed |  |
| Grant Funding | 27 June 2024 | Substantial Opinion | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  |
| Medium Term Financial Planning | 18 September 2024 | Substantial Opinion | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |
| Asset Management | 30 October 2024 | Moderate Opinion | 0 | 1 | 3 | 0 | 3 | 0 | 1 |  |
| Joint Core Financials | 27 November 2024 | Moderate Opinion | 0 | 2 | 3 | 0 | 0 | 0 | 5 |  |
| Workforce Planning | 27 February 2025 | Moderate Opinion | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  |
| Business Continuity & Emergency Planning Follow Up | 29 May 2025 | n/a | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  |
| Procurement and Supply Chain | 18 June 2025 | Moderate Opinion | 0 | 2 | 1 | 0 | 0 | 0 | 3 |  |
| Joint Governance | 03 July 2025 | Moderate Opinion | 0 | 1 | 2 | 1 | 0 | 0 | 2 |  |
| Police and Fire IT Governance | 29 July 2025 | Moderate Opinion | 0 | 2 | 2 | 0 | 0 | 0 | 4 |  |
| Joint Estates Management | 22 August 2025 | Moderate Opinion | 0 | 1 | 0 | 0 | 1 | 0 | 0 |  |
| Totals |  |  | 1 | 11 | 11 | 1 | 4 | 0 | 18 |  |

| 2025/26 Audits | Date | Grade | Recommendations |  |  |  |  |  |  | Overall Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Priority 1 | Priority 2 | Priority 3 | Progress |  |  |  |  |
|  |  |  |  |  |  | Overdue | Revised | Ongoing | Closed |  |
| Seized Property | 24 October 2025 | Substantial Opinion | 0 | 0 | 2 | 0 | 0 | 0 | 2 |  |
| Joint Fleet Management | 30 October 2025 | Moderate Opinion | 0 | 2 | 2 | 2 | 0 | 2 | 0 |  |
| Accreditation Management | 21 November 2025 | Limited Opinion | 1 | 1 | 2 | 0 | 0 | 4 | 0 |  |
| Control Room & First Contact | 17 February 2026 | Substantial Opinion | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |
| Totals |  |  | 1 | 3 | 6 | 2 | 0 | 6 | 2 |  |

Full details of all audit recommendations are in the Summary of Internal Audit Recommendations report below.

  - New Audits

Since the last report to JIAC four audits have been completed, making ten recommendations.

  - Overdue Recommendations

Three recommendations have passed their implementation dates and remain outstanding.

| Audit | Recommendation | Update | Original Date |
| --- | --- | --- | --- |
| Joint Governance – July 2025 | Recommendation 2 – OPFCC and Force – Policy and procedure review | The Head of Office is pulling a list together of the policies and procedures that require a review and then these will be allocated for review to appropriate staff members. – Update 16/02/26 The action relating to having a more comprehensive list of policy with identified review dates is completed. The policies relating to matters concerning HR have been collated and are with HR colleagues for review with the intention of merging these wherever possible with those of Northamptonshire Police. This work sits at the moment with a business manager in HR to take forward on our behalf. No current timescale for this work. Non HR based policy will in the future be taken to OPFCC SMT once a month to enable a three month forward plan for those matters that need review. | 30 Oct 25 |
| Joint Fleet Management – October 2025 | Recommendation 1 - Force and Fire do not currently have a Fleet Management Strategy and supporting Implementation Plans in place | The Department shall be publishing a joint Asset Strategy which shall consolidate and have a single fleet strategy. This shall then be used to support deliverables across the capital replacement, Policing Plan and CMRP. The work is underway to ensure in year actions are identified and reported upon. No updates received but links to the Asset Strategy that has now been presented to Fire SLT and FEM. Expected to be published by end of February 26. | 31 Dec 25 |
| Joint Fleet Management – October 2025 | Recommendation 4 - Engagement with sector Fleet Groups | This is supported and is aligned to temporary responsibilities role; this shall be part of the future role under the restructure. No updates received but links to the Asset Strategy that has now been presented to Fire SLT and FEM. Expected to be published by end of February 26. | 31 Dec 25 |

  - Recommendations With Revised Implementation Dates

Six recommendations have revised implementation dates.

| Audit | Recommendation | Update | Original Date | Revised Date |
| --- | --- | --- | --- | --- |
| Identity Access Management – June 2024 | Recommendation 2 - Multifactor Authentication for Fire AD Accounts | The mobile phone paper was presented to Fire SLT in late November, and they requested further work to define the different roles within Fire and identify the appropriate technology requirements for each role before approving the proposal to issue mobile phones to all users. | 31 Dec 25 | 31 Dec 26 |
| Identity Access Management – June 2024 | Recommendation 4 - Password Management Tool Implementation | The procurement process has now progressed, and this will be a direct award vis the Northants IT framework. DDaT will await contract details once finalised. On track | 31 Mar 25 | 01 Oct 26 |
| Asset Management – October 2024 | Recommendation 1 - Lack of Equipment and Inventory Checks | The workstreams to support this is now embedded and work is underway to validate the data in Redkite. The actions need to be realigned to allow for consultation, staff moves and then commencement. | 30 Nov 25 | 31 Aug 26 |
| Asset Management – October 2024 | Recommendation 2 - Lack of updated policies and procedures. | The policy has now been presented to Fire SLT and the Force Executive Meeting. Commentary received back has been minimal and will be reviewed with ACO before publication. | 30 Sep 25 | 28 Feb 26 |
| Asset Management – October 2024 | Recommendation 3 - Lack of equipment testing. | As above for recommendation 1 | 30 Nov 25 | 31 Aug 26 |
| Joint Estates Management – August 2025 | Recommendation 1 - Completion of stock condition surveys | Owing to delays in finalising the estates delivery plan, and increased volumes of work against a backdrop of reduced capacity in Q3 25/26 this shall need to be pushed back until end of Q1 26/27 – pending confirmation of Commercial and Property P1s | 30 Jan 26 | 30 Jun 26 |

  - Completed Recommendations

Fourteen recommendations have been completed since the last report to JIAC.

| Audit | Recommendation | Update |
| --- | --- | --- |
| Identity Access Management – June 2024 | Recommendation 1 - Lack of Periodic User Access Reviews | Having reviewed the original audit scope, the focus of this recommendation was to implement a regular regimen of Windows AD access reviews. The sys admin team now have consistent scripts running that identify changes such as add or removal to AD accounts. |
| Identity Access Management – June 2024 | Recommendation 5 - Completion of Access Changes | This audit action is linked to ITSM platform development, which has progressed significantly with core capabilities in place, including automated handling of access-related documentation and updated procedures for manual attachment where required. |
| IT Asset Legacy Management – June 2024 | Recommendation 1 - Automated scanning of hardware and software is not used to identify inaccuracies in the IT asset register | Automated scanning of hardware and software to identify inaccuracies in the IT asset register has been addressed through ITSM platform development, with key components such as SSO, APIs, and asset uploads implemented. |
| Asset Management – October 2024 | Recommendation 4 - Reliance on spreadsheet for the Vehicle Maintenance and Records | The provision of Appliance maintenance has now transferred to the external contractor, and we have now moved onto their approved system to manage all the relevant records for maintenance of the fleet. Internal processes have also been reviewed and amended in line with JOT to ensure timely and efficient management of servicing and maintenance. |
| Workforce Planning – February 2025 | Recommendation 1 – No formal succession plans for critical roles | Further responses received from departments and collated into spreadsheet showing roles and identified scoring. Further meeting scheduled for 4th February with Workforce Planning to review list and confirm those roles considered critical. this is a starting point, and a review will be conducted on a regular basis and other roles added / removed as required. Work has been ongoing to identify a mechanism for succession planning to the critical roles and an additional box will appear on the talent tile with the ability to select any of the critical roles. This process will be implemented with the start of the new PDR in April 2026. |
| Business Continuity & Emergency Planning Follow Up | Recommendation 1 - Annual Testing Programme | All plans continue to be exercised on a rolling basis. |
| Procurement and Supply Chain – June 2025 | Recommendation 1 - Sending timely reminders to suppliers within frameworks | The additional administrative resource is now in place and processes have been revisited to ensure consistency of approach. In addition to the internal processes, the expectations for suppliers have been strengthened within the framework paperwork for the new pensions framework and has been clearly outlined to all new suppliers for the IT framework. The improvements against this objective will be monitored and quality assured over the next 12 months. |
| Joint Governance – July 2025 | Recommendation 1 - Chief Fire Officer’s expenses not published online | This is done on a monthly or bi-monthly basis and is published on the NFRS website. |
| Police and Fire IT Governance – July 2025 | Recommendation 1 - Lack of an Organisational Cyber Security Policy | Draft completed and presented to Chief Digital Officer in October 2025. |
| Police and Fire IT Governance – July 2025 | Recommendation 2 - Lack of Consolidated Portfolio Planning | There was an agreement with CFO and paper to SLT in Sept last year on how projects would be managed in Fire; review held with CFO that agreed the approach (23/8/24). This governance has been implemented ACFO Jim Powell has introduced and chairs a Fire Change Improvement Board (CIB). Members include Fire SLT and DDaT. |
| Police and Fire IT Governance – July 2025 | Recommendation 3 - Unclear links between governance bodies | The intent of this action has been addressed through the organisational restructure and the introduction of ES-wide tasking and tracking meetings. These mechanisms ensure DDaT governance is integrated within wider governance. |
| Police and Fire IT Governance – July 2025 | Recommendation 4 - Data Quality Assurance Procedure | Data quality strategies for both organisation have been drafted and disseminated for review and comment. The data quality working group continues to drive best practice and oversight of all data quality activities in both organisations, and there remains an escalation process within both organisations |
| Seized Property - October 2025 | Recommendation 1 - Cash Exhibit Handling and Location Discrepancies | All actions were completed following the audit. |
| Seized Property - October 2024 | Recommendation 2 - Discrepancy Between Niche Listings and Physical Locations | - Reinforce training for officers - L&D contacted to offer to review training and provide further guidance if required. EP Team already remind officers of the EP process during briefing sessions. - Continue to perform weekly audits - Already in place on ongoing. - Introduce a mandatory check-out protocol for officers - There are signs to remind officers to check out any items they remove from stores. This is also covered in briefings given to officers and a reminder is to be issued on ForceNet. The EP team conduct regular audits to identify any missing items. |

- COLLABORATION AUDITS

  - Overall Status

| 2024/25 Audits | Date | Grade | Recommendations |  |  |  |  |  |  | Overall Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Priority 1 | Priority 2 | Priority 3 | Progress |  |  |  |  |
|  |  |  |  |  |  | Overdue | Revised | Ongoing | Closed |  |
| EMSOU – Data Governance and Security | 11 April 2025 | Substantial Opinion | 0 | 1 | 1 | 1 | 0 | 0 | 1 |  |
| EMSOU – Wellbeing & EDI | 29 May 2025 | Moderate Opinion | 0 | 2 | 2 | 0 | 0 | 4 | 0 |  |
| Totals |  |  | 0 | 3 | 3 | 1 | 0 | 4 | 1 |  |

  - Overdue Recommendations

One recommendation has passed its implementation date and remains outstanding.

| Audit | Recommendation | Update | Original Date |
| --- | --- | --- | --- |
| EMSOU – Data Governance and Security – April 2025 | Recommendation 1 - Incomplete Information Asset Register | EMSOU should ensure that the information asset registers are kept updated and that information owners are clear on their responsibilities in completing all relevant sections. Action agreed. Update requested but not yet received. | 01 Jul 25 |

  - Completed Recommendations

One recommendation has been completed since the last report to JIAC.

| Audit | Recommendation | Update |
| --- | --- | --- |
| EMSOU – Data Governance and Security – April 2025 | Recommendation 2 - Security Handbook Not Updated | EMSOU should ensure that Security Handbook is updated on a regular basis, and that contact details of members of staff is accurate. Action agreed. Update 01/07/25 - Handbook has been updated |

EQUALITY, DIVERSITY AND HUMAN RIGHTS IMPLICATIONS

None

#### HUMAN RESOURCES IMPLICATIONS

None

#### RISK MANAGEMENT IMPLICATIONS

None.

#### ENVIRONMENTAL IMPLICATIONS

None

Author:				Richard Baldwin,

Business Continuity and Risk Manager

Chief Officer Portfolio Holder:	Paul Bullen, Assistant Chief Officer

Background Papers:	Summary of Internal Audit Recommendations for JIAC March 2026.