### Report to the Joint Independent Audit Committee

### 07 October 2026

Internal Audit Recommendations Summary Report

RECOMMENDATION

The Committee is asked to note this report.

### PURPOSE OF THE REPORT

  - This report provides the Joint Independent Audit Committee (JIAC) with an update on the status of actions arising from recommendations made in internal audit reports.

  - The report contains actions arising from audits of Northamptonshire Police and the Office of Northamptonshire Police, Fire and Crime Commissioner and East Midlands Collaboration Units. Where joint police and fire audits have been undertaken all recommendations are included in this report irrespective of whether they apply solely to police or fire or if they apply jointly to both organisations.

  - The attached Summary of Internal Audit Recommendations Report shows details and the current status of all open audit actions.

  - The Risk, Audit and Assurance Board has oversight of all outstanding audit actions and directs the activities required to complete any actions that have passed their targeted implementation date.

- NORTHAMPTONSHIRE AUDITS

  - Overall Status

Overview of completed internal audits and recommendations by audit year.

| 2023/24 Audits | Date | Grade | Recommendations |  |  |  |  |  |  | Overall Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Priority 1 | Priority 2 | Priority 3 | Progress |  |  |  |  |
|  |  |  |  |  |  | Overdue | Revised | Ongoing | Closed |  |
| Firearms Licensing | 21 July 2023 | Moderate Assurance | 0 | 2 | 0 | 0 | 0 | 0 | 2 |  |
| RUI Follow Up | 26 September 2023 | Moderate Assurance | 0 | 1 | 2 | 0 | 0 | 0 | 3 |  |
| Business Continuity & Emergency Planning | 01 November 2023 | Limited Assurance | 2 | 3 | 0 | 0 | 0 | 0 | 5 |  |
| Reasonable Adjustments Follow Up | 25 January 2024 | Moderate Assurance | 0 | 2 | 3 | 0 | 0 | 0 | 5 |  |
| Core Financials | 06 March 2024 | Moderate Assurance | 0 | 3 | 3 | 0 | 0 | 0 | 6 |  |
| Vetting | 18 March 2024 | Moderate Assurance | 0 | 1 | 2 | 0 | 0 | 0 | 3 |  |
| Fleet Management Follow Up | 25 April 2024 | Moderate Assurance | 0 | 0 | 3 | 0 | 0 | 0 | 3 |  |
| Payroll | 01 May 2024 | Moderate Assurance | 0 | 3 | 0 | 0 | 0 | 0 | 3 |  |
| Identity Access Management | 11 June 2024 | Limited Opinion | 0 | 5 | 1 | 0 | 2 | 0 | 4 |  |
| IT Asset Legacy Management | 11 June 2024 | Moderate Opinion | 0 | 2 | 3 | 0 | 0 | 0 | 5 |  |
| Totals |  |  | 2 | 22 | 17 | 0 | 2 | 0 | 39 |  |

| 2024/25 Audits | Date | Grade | Recommendations |  |  |  |  |  |  | Overall Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Priority 1 | Priority 2 | Priority 3 | Progress |  |  |  |  |
|  |  |  |  |  |  | Overdue | Revised | Ongoing | Closed |  |
| Grant Funding | 27 June 2024 | Substantial Opinion | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  |
| Medium Term Financial Planning | 18 September 2024 | Substantial Opinion | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |
| Asset Management | 30 October 2024 | Moderate Opinion | 0 | 1 | 3 | 0 | 3 | 0 | 1 |  |
| Joint Core Financials | 27 November 2024 | Moderate Opinion | 0 | 2 | 3 | 0 | 0 | 0 | 5 |  |
| Workforce Planning | 27 February 2025 | Moderate Opinion | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  |
| Business Continuity & Emergency Planning Follow Up | 29 May 2025 | n/a | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  |
| Procurement and Supply Chain | 18 June 2025 | Moderate Opinion | 0 | 2 | 1 | 0 | 0 | 0 | 3 |  |
| Joint Governance | 03 July 2025 | Moderate Opinion | 0 | 1 | 2 | 0 | 1 | 0 | 2 |  |
| Police and Fire IT Governance | 29 July 2025 | Moderate Opinion | 0 | 2 | 2 | 0 | 0 | 0 | 4 |  |
| Joint Estates Management | 22 August 2025 | Moderate Opinion | 0 | 1 | 0 | 0 | 1 | 0 | 0 |  |
| Totals |  |  | 1 | 11 | 11 | 0 | 5 | 0 | 18 |  |

| 2025/26 Audits | Date | Grade | Recommendations |  |  |  |  |  |  | Overall Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Priority 1 | Priority 2 | Priority 3 | Progress |  |  |  |  |
|  |  |  |  |  |  | Overdue | Revised | Ongoing | Closed |  |
| Seized Property | 24 October 2025 | Substantial Opinion | 0 | 0 | 2 | 0 | 0 | 0 | 2 |  |
| Joint Fleet Management | 30 October 2025 | Moderate Opinion | 0 | 2 | 2 | 0 | 1 | 0 | 3 |  |
| Accreditation Management | 21 November 2025 | Limited Opinion | 1 | 1 | 2 | 0 | 0 | 4 | 0 |  |
| Control Room & First Contact | 17 February 2026 | Substantial Opinion | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |
| Freedom of Information & Subject Access Requests | 13 March 2026 | Limited Opinion | 1 | 3 | 3 | 0 | 2 | 0 | 5 |  |
| Joint Core Financials | 23 April 2026 | Moderate Opinion | 0 | 3 | 3 | 0 | 1 | 1 | 4 |  |
| Digital Forensics Unit | 07 May 2026 | Moderate Opinion | 0 | 3 | 2 | 0 | 0 | 1 | 4 |  |
| Legacy Systems Management | 17 June 2026 | Moderate Opinion | 0 | 1 | 1 | 0 | 0 | 2 | 0 |  |
| Misconduct Hearings | 24 June 2026 | Moderate Opinion | 0 | 3 | 1 | 0 | 0 | 4 | 0 |  |
| Totals |  |  | 2 | 16 | 16 | 0 | 4 | 12 | 18 |  |

Full details of all audit recommendations are in the Summary of Internal Audit Recommendations report below.

  - New Audits

Since the last report to JIAC five audits have been completed, making twenty-four recommendations.

  - Overdue Recommendations

No recommendations have passed their implementation dates and remain outstanding.

| Audit | Recommendation | Update | Original Date |
| --- | --- | --- | --- |

  - Recommendations With Revised Implementation Dates

Eleven recommendations have revised implementation dates.

| Audit | Recommendation | Update | Original Date | Revised Date |
| --- | --- | --- | --- | --- |
| Identity Access Management – June 2024 | Recommendation 2 - Multifactor Authentication for Fire AD Accounts | The mobile phone paper was presented to Fire SLT in late November, and they requested further work to define the different roles within Fire and identify the appropriate technology requirements for each role before approving the proposal to issue mobile phones to all users. | 31 Dec 25 | 31 Dec 26 |
| Identity Access Management – June 2024 | Recommendation 4 - Password Management Tool Implementation | The procurement process has now progressed, and this will be a direct award vis the Northants IT framework. DDaT will await contract details once finalised. On track | 31 Mar 25 | 01 Oct 26 |
| Asset Management – October 2024 | Recommendation 1 - Lack of Equipment and Inventory Checks | The workstreams to support this is now embedded and work is underway to validate the data in Redkite. The actions need to be realigned to allow for consultation, staff moves and then commencement. | 30 Nov 25 | 31 Aug 26 |
| Asset Management – October 2024 | Recommendation 2 - Lack of updated policies and procedures. | The policy has now been presented to Fire SLT and the Force Executive Meeting. Commentary received back has been minimal and will be reviewed with ACO before publication. | 30 Sep 25 | 28 Feb 26 |
| Asset Management – October 2024 | Recommendation 3 - Lack of equipment testing. | As above for recommendation 1 | 30 Nov 25 | 31 Aug 26 |
| Joint Governance – July 2025 | Recommendation 2 - OPFCC and Force – Policy and procedure review | Full list of policies now completed and all have either been reviewed or are in the process of review. This will be an ongoing commitment. As a part of this review there will be a requirement to ensure that the policy reviewed is not only current and up to date but has a scheduled review period relating to it. All of the specific policies that are referred to in this audit action as requiring updates have been completed. | 30 Oct 25 | 31 Oct 26 |
| Joint Estates Management – August 2025 | Recommendation 1 - Completion of stock condition surveys | Following the reprioritisation of the Priority programmes for the Property team and the need to focus on P1s this work was placed on Hold. This shall now be commenced in FY26/27. Surveys shall be procured and commenced. | 30 Jan 26 | 31 Mar 27 |
| Joint Fleet Management – October 2025 | Recommendation 2 - Force vehicles are not always serviced in line with servicing schedule guidance | The team have been updating records however, following work with external suppliers it has been identified that some of the process can be automated. The team have held a series of workshops to look at improving efficiency and effectiveness. Final training scheduled for June 2026 to then enable more electronic rather than manual process. | 31 Mar 26 | 31 Dec 26 |
| Freedom on Information and Subject Access Requests – March 2026 | Recommendation 1 - Timeliness of FOI and SAR responses | FOI backlog recovery has continued and would have been cleared; however, assurance activity identified a number of FOI requests that had been erroneously closed and require remediation. Further review of the legacy Cyclops system identified an additional cohort of approximately 69-70 potentially affected FOI cases beyond those previously reported, requiring further validation and reconciliation. SAR performance continues to improve, with outstanding SARs reducing from 353 to 313 and the SAR backlog reducing from 276 to 208 between 29 June and 27 July 2026. FOI performance has also improved, with the FOI backlog reducing from 274 to 160 over the same period. The Force is also engaging with the ICO regarding these matters and is expecting formal regulatory action in the form of an Enforcement Notice. Recovery activity, governance oversight and performance improvement work remain ongoing. | 01 Jul 26 | 31 Dec 26 |
| Freedom on Information and Subject Access Requests – March 2026 | Recommendation 3 – Public Disclosure of FOIs | Publication has started but this needs dedicated resource to maintain ongoing updates - recruitment for an admin post to manage this is in progress. | 01 Jul 26 | 31 Dec 26 |
| Joint Core Financials – April 2026 | Recommendation 5 - Lack of contingency in place for when individuals signing off reconciliations are away. | We will work in the team to ensure that all reconciliations are reviewed across the managers in the team to ensure segregation of duties | 30 Jun 26 | 31 Dec 26 |

  - Completed Recommendations

Sixteen recommendations have been completed since the last report to JIAC.

| Audit | Recommendation | Update |
| --- | --- | --- |
| Joint Fleet Management – October 2025 | Recommendation 1 - Force and Fire do not currently have a Fleet Management Strategy and supporting Implementation Plans in place. | The new Joint Asset Strategy has now been signed off and published. |
| Joint Fleet Management – October 2025 | Recommendation 3 - The Force does not always close down open job cards on the TranMan system | At the time of the audit, the team were carrying several vacancies which contributed to the Tranman records not having up to date records. Team members are in place to now support in ensuring records updated. The force has now established a Fleet working group to mirror a similar provision within Fire. This shall then ensure issues and performance data can be reviewed and monitored. |
| Joint Fleet Management – October 2025 | Recommendation 4 - Engagement with sector Fleet Groups | This is supported and is aligned to temporary responsibilities role; this will be part of the future role under the restructure. |
| Freedom on Information and Subject Access Requests – March 2026 | Recommendation 2 - Human error regarding redaction of SARs | Enhanced quality assurance and governance controls have been implemented across the SAR process to reduce the risk of human error during redaction activities. Additional management oversight, case review processes and performance monitoring have been embedded within operational practice, with no recurring systemic issues identified through ongoing assurance activity. The controls implemented provide increased confidence in the accuracy and consistency of SAR disclosures and have been incorporated into business-as-usual processes. |
| Freedom on Information and Subject Access Requests – March 2026 | Recommendation 4 - Lack of formal reporting mechanisms for Security Audits | All previous audit recommendations have been implemented and tracked to completion. The annual audit plan has been approved, and Information Assurance management packs are being developed to provide ongoing oversight of audit recommendations, action owners and due dates. Whilst further improvements have been identified, these relate to continuous service improvement rather than audit non-compliance. A review of the process will be undertaken during Autumn 2026 to identify opportunities to further strengthen efficiency, governance and quality assurance arrangements. |
| Freedom on Information and Subject Access Requests – March 2026 | Recommendation 5 - Completing received and due date fields within ADISCO | Processes and quality assurance checks have been implemented to ensure received dates and statutory due dates are recorded within ADISCO, improving case tracking, management oversight and performance reporting. Compliance with recording requirements is now monitored through routine governance processes and has been embedded into business-as-usual activity. While ADISCO is not a fully fit-for-purpose case management solution and there remains a longer-term ambition to move to a more suitable system, the current controls provide an appropriate and proportionate mitigation within the existing operating environment. |
| Freedom on Information and Subject Access Requests – March 2026 | Recommendation 6 - Updating policies and procedures | All policies are now updated and live on the Policy Library. |
| Freedom on Information and Subject Access Requests – March 2026 | Recommendation 7 - Ensuring Training is completed by Information Management Unit Staff | The training needs assessment is now complete, funding secured and training providers engaged with to deliver tailored and appropriate training for disclosure officers and records management staff. |
| Joint Core Financials – April 2026 | Recommendation 1 - Expense claims without sufficient evidence being made within Force and Fire | This is still being investigated with our payroll provider to see if mandatory fields are possible (this has been discussed but nothing implemented) however the team continue to audit claims. |
| Joint Core Financials – April 2026 | Recommendation 2 - No Approval process for Force overtime claims | Nothing has changed within finance on this and we continue to review large payments. There is a push within the force to have overtime signed off by supervisors however nothing has been implemented with this as yet. |
| Joint Core Financials – April 2026 | Recommendation 3 - Timely creation of supplier accounts and invoices. | Training for the team is undertaken and ongoing so whilst a due date of the 31st March was set this is an ongoing action. |
| Joint Core Financials – April 2026 | Recommendation 6 - No automated workflow in place for changes in email address for fire suppliers. | Workflow adjustments were implemented at the end of August and we will ask internal audit to re review this to ensure all areas are covered. |
| Digital Forensics Unit – May 2026 | Recommendation 1 - The Digital Forensic Policy and Digital Forensic Procedure require updates. | The Policy and Procedures have both been updated and published. |
| Digital Forensics Unit – May 2026 | Recommendation 2 - Training compliance rates are not tracked. | We have records on the L&D system showing who is PIP1 trained. There will always be a percentage of officers who have no record because as stated, they transferred in from a Force who may have called the training something else. They are all benchmarked during a mentoring/tutoring period to ensure the standards are met. PIP1 training is a requirement for all officers involved in investigations who would be listed as Frontline on the agreed roles held in L&D. All Detectives are qualified to PIP2. The PIP2 CPD policy went live earlier this year ensuring that we have, as HMIC requires, a list of active and inactive PIOP2 investigators. This is recorded on the L&D system and is reported back to Detective Governance. Monitoring attendance and completion of courses can be achieved through the L&D system. DEMS training is being developed and we can report on the percentages completed. CPD and competence levels are TBA via the DEMS training group designing the training to achieve the Forensic Regulators requirements. |
| Digital Forensics Unit – May 2026 | Recommendation 3 - Exhibit locations on Niche and LANDesk do not align. | The Working Instruction has been revised to include updating Niche. A reminder has been issued to all staff to record the LANDesk reference number. |
| Digital Forensics Unit – May 2026 | Recommendation 5 - Higher privilege licenses in LANDesk are not reviewed on a regular basis. | Audit of LANDesk access completed in July. Further audits will be requested at 6 month intervals. |

- COLLABORATION AUDITS

  - Overall Status

| 2024/25 Audits | Date | Grade | Recommendations |  |  |  |  |  |  | Overall Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Priority 1 | Priority 2 | Priority 3 | Progress |  |  |  |  |
|  |  |  |  |  |  | Overdue | Revised | Ongoing | Closed |  |
| EMSOU – Data Governance and Security | 11 April 2025 | Substantial Opinion | 0 | 1 | 1 | 1 | 0 | 0 | 1 |  |
| EMSOU – Wellbeing & EDI | 29 May 2025 | Moderate Opinion | 0 | 2 | 2 | 1 | 0 | 0 | 3 |  |
| Totals |  |  | 0 | 3 | 3 | 2 | 0 | 0 | 4 |  |

| 2025/26 Audits | Date | Grade | Recommendations |  |  |  |  |  |  | Overall Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Priority 1 | Priority 2 | Priority 3 | Progress |  |  |  |  |
|  |  |  |  |  |  | Overdue | Revised | Ongoing | Closed |  |
| EMSOU – POCA Income | 10 March 2026 | Moderate Opinion | 0 | 1 | 2 | 0 | 0 | 0 | 3 |  |
| EMSOU Forensics Accreditation | 14 May 2026 | Substantial Opinion | 0 | 0 | 1 | 0 | 0 | 1 | 0 |  |
| Totals |  |  | 0 | 1 | 3 | 0 | 0 | 1 | 3 |  |

  - Overdue Recommendations

Two recommendations have passed their implementation dates and remain outstanding.

| Audit | Recommendation | Update | Original Date |
| --- | --- | --- | --- |
| EMSOU – Data Governance and Security – April 2025 | Recommendation 1 - Incomplete Information Asset Register | Information Asset Register/Records of Processing is now placed on the MS365 Sharepoint list. Further work is required as there is duplication which needs to be understood and amended accordingly. | 01 Jul 25 |
| EMSOU Wellbeing and EDI – May 2025 | Recommendation 2 - Nil response and disclosure rate targets | Ethnicity/ Group data - currently doing a complete rebuild of HR GATEWAY records to ensure we have information from all EMSOU forces. This means we will have full 'Partner' records for officers from Lincs, Notts, Nhants - records that we hold limited information on currently. In addition, we have shared 'Safe to Share' campaign and will be launching an EMSOU 'update your personal record' in Feb-March 2026. We report on diversity date on at least a 2-monthly basis for current staff. As of Jan 2026 = ROCU - 865fte of which we are missing diversity data as follows: - Ethnicity - 97% (19 colleagues data is 'Unknown/ Prefer not to say') - Gender - 100% - Age - 100% - Disability - 48% (417 people) have not stated whether they have disability or not (so its blank in the field) - Sexuality – 55% (473 people) have not stated their sexuality (so its blank in the field) plus 2% have said they ‘Prefer not to say’ We are working with HRSSC to ensure that this information is carried over from the recruitment record to the full employment record/ partner records. In addition, we are currently awaiting reporting from the HR Shared Service Centre to understand where/ if there are potential 'glass ceilings' for our recruitment processes. We hope to have this data in Q4 2025/26. | 31 Mar 26 |

  - Completed Recommendations

Six recommendations have been completed since the last report to JIAC.

| Audit | Recommendation | Update |
| --- | --- | --- |
| EMSOU Wellbeing and EDI – May 2025 | Recommendation 1 - The Unit does not maintain sufficient oversight of the implementation status of actions within the People Strategy. | We report on progress against People Plan at People Board that follows each Quarter (just done it in Jan for Q3). The update shows progress to date and we also highlight additional activity that has needed to take priority/ a rationale why things have not been delivered. |
| EMSOU Wellbeing and EDI – May 2025 | Recommendation 3 - Wellness newsletters are currently not being circulated. | Rather than create the ‘State Four’ e-magazine we have continued to develop our intranet Health & Wellbeing Hub and Inclusion, Diversity & Equality Hub to provide a single, reliable place for colleagues to access support. This ensures that updates and resources are clearly communicated and also reduces the need for users to search multiple systems or rely on a monthly email pdf attachment, which isn’t ‘searchable’. This aims to improve visibility of available services and encourages a more proactive approach to wellbeing and inclusion. The hub also offers valuable insights by tracking popular resources and engagement, helping us shape future wellbeing and inclusion activity. |
| EMSOU Wellbeing and EDI – May 2025 | Recommendation 4 - Trends and themes regarding staff leavers are not circulated to senior management on a regular basis. | Leavers data - presented on a 2-monthly basis. |
| EMSOU POCA Income – March 2026 | Recommendation 1 - Lack of records provided or communication with auction house once asset is sold. | A formal process within EMSOU has been introduced requiring all joint investigations to be governed by a Memorandum of Understanding (MOU), which must be agreed and signed prior to the commencement of the investigation. The MOU will cover an agreed communication channel between all parties. It will also clearly set out asset management procedures, covering the full lifecycle from seizure through to final realisation. The document incorporates appropriate oversight by the Head of Department to ensure compliance, governance, and accountability throughout the investigation. |
| EMSOU POCA Income – March 2026 | Recommendation 2 – Lack of record of sold assets. | The EMSOU Standard Operating Procedure (SOP) for asset management has been fully rewritten. It now requires that records of sale are retained to demonstrate value for money and confirms that appropriate access to approved sale portals has been secured. |
| EMSOU POCA Income – March 2026 | Recommendation 3 - Reconciliation procedure not updated | The procedure document has been reviewed and adequate controls have been put in place to ensure a yearly review takes place. |

EQUALITY, DIVERSITY AND HUMAN RIGHTS IMPLICATIONS

None

#### HUMAN RESOURCES IMPLICATIONS

None

#### RISK MANAGEMENT IMPLICATIONS

None.

#### ENVIRONMENTAL IMPLICATIONS

None

Author:				Richard Baldwin,

Business Continuity and Risk Manager

Chief Officer Portfolio Holder:	Paul Bullen, Assistant Chief Officer

Background Papers:	Summary of Internal Audit Recommendations for JIAC October 2026.